## gantt_table_hard
Name | Task | Time (h) | Dependencies | Human Resources | Type | Start | End | Duration
Project Management | T1 | 136 |  |  | PM
Tutor Meetings | T1.1 | 10 | - | PM, AIC | PM | 2023-01-02 | 2023-05-01 | 119
Contextualisation and Scope | T1.2 | 15 | - | PM,DS | PM | 2023-01-02 | 2023-01-07 | 5
Project Planning | T1.3 | 12 | T1.2 | PM | PM | 2023-01-07 | 2023-01-10 | 3
Economic Management | T1.4 | 12 | T1.3 | PM | PM | 2023-03-02 | 2023-03-11 | 9
Sustainability Report | T1.5 | 12 | T1.4 | PM | PM | 2023-03-11 | 2023-03-15 | 4
Final Document Synthesis | T1.6 | 40 | T1.5, T4.1, T4.2 | PM | PM | 2023-01-02 | 2023-05-01 | 119
Development Monitoring | T1.7 | 35 | - | PM | PM | 2023-01-02 | 2023-05-01 | 119
Research | T2 | 200 |  |  | RE
Study transformer Architecture | T2.1 | 60 | T1.2 | DS | RE | 2023-01-10 | 2023-02-20 | 41
Familiarise with NLP techniques | T2.2 | 50 | T1.2 | DS | RE | 2023-01-10 | 2023-02-20 | 41
Analyse Music Datasets | T2.3 | 50 | T1.2 | DS | RE | 2023-01-10 | 2023-02-20 | 41
Explore Deep Learning Frameworks | T2.4 | 20 | T2.1, T2.2 | DS | RE | 2023-02-20 | 2023-03-02 | 10
Investigate web development stacks | T2.5 | 20 | - | FSD | RE | 2023-02-20 | 2023-03-02 | 10
Development and Experimentation | T3 | 100 |  |  | DE
Create Development Environments | T3.1 | 5 | T2.4, T2.5 | DS | DE | 2023-03-15 | 2023-03-19 | 4
Exploratory Data Analysis (EDA) | T3.2 | 10 | T2.3, T3.1 | DS | DE | 2023-03-19 | 2023-03-23 | 4
Build Experimentation Pipeline | T3.3 | 20 | T3.2 | DS | DE | 2023-03-23 | 2023-03-28 | 5
Train Model | T3.4 | 25 | T3.3 | DS | DE | 2023-03-28 | 2023-04-05 | 8
Fine-tune Model | T3.5 | 10 | T3.4 | DS | DE | 2023-04-05 | 2023-04-20 | 15
Design User Interface | T3.6 | 10 | - | FSD | DE | 2023-03-15 | 2023-03-19 | 4
Implement User Interface | T3.7 | 10 | T3.6, T3.1 | FSD | DE | 2023-03-19 | 2023-03-23 | 4
Program API Server | T3.8 | 5 | T3.1 | FSD | DE | 2023-04-05 | 2023-04-20 | 15
Deploy web application | T3.9 | 5 | T3.8, T3.7 | FSD | DE | 2023-03-28 | 2023-04-05 | 8
Testing and Evaluation | T4 | 40 |  |  | TE
Evaluate Model | T4.1 | 20 | T3.4, T3.5 | DS, AIC | TE | 2023-04-20 | 2023-05-01 | 11
Test User Interface Design | T4.2 | 20 | T3.9 | FSD | TE | 2023-04-20 | 2023-05-01 | 11
Formulas:
Duration = DATEDIF([Start], [End], "D")

## gantt_table_automatic
Name | Task | Time (h) | Dependencies | Human Resources | Type | Start | End | Completion
Project Management | T1 | 136 |  |  | PM | 2023-01-02 | 2023-05-01
Tutor Meetings | T1.1 | 10 | - | PM, AIC | PM | 2023-01-02 | 2023-01-07
Contextualisation and Scope | T1.2 | 15 | - | PM,DS | PM | 2023-01-07 | 2023-01-10
Project Planning | T1.3 | 12 | T1.2 | PM | PM | 2023-03-07 | 2023-03-11
Economic Management | T1.4 | 12 | T1.3 | PM | PM | 2023-03-11 | 2023-03-15
Sustainability Report | T1.5 | 12 | T1.4 | PM | PM | 2023-01-02 | 2023-05-01
Final Document Synthesis | T1.6 | 40 | T1.5, T4.1, T4.2 | PM | PM | 2023-01-02 | 2023-05-01
Development Monitoring | T1.7 | 35 | - | PM | PM
Research | T2 | 200 |  |  | RE | 2023-01-10 | 2023-01-30
Study transformer Architecture | T2.1 | 60 | T1.2 | DS | RE | 2023-01-10 | 2023-01-30
Familiarise with NLP techniques | T2.2 | 50 | T1.2 | DS | RE | 2023-01-10 | 2023-01-30
Analyse Music Datasets | T2.3 | 50 | T1.2 | DS | RE | 2023-01-30 | 2023-02-04
Explore Deep Learning Frameworks | T2.4 | 20 | T2.1, T2.2 | DS | RE | 2023-01-30 | 2023-02-04
Investigate web development stacks | T2.5 | 20 | - | FSD | RE
Development and Experimentation | T3 | 100 |  |  | DE | 2023-02-04 | 2023-02-08
Create Development Environments | T3.1 | 5 | T2.4, T2.5 | DS | DE
Exploratory Data Analysis (EDA) | T3.2 | 10 | T2.3, T2.2 | DS | DE
Build Experimentation Pipeline | T3.3 | 20 | T3.2 | DS | DE
Train Model | T3.4 | 25 | T3.3 | DS | DE
Fine-tune Model | T3.5 | 10 | T3.4 | DS | DE | 2023-02-04 | 2023-02-08
Design User Interface | T3.6 | 10 | - | FSD | DE
Implement User Interface | T3.7 | 10 | T3.6, T3.1 | FSD | DE
Program API Server | T3.8 | 5 | T3.1 | FSD | DE
Deploy web application | T3.9 | 5 | T3.8, T3.7 | FSD | DE
Testing and Evaluation | T4 | 40 |  |  | TE
Evaluate Model | T4.1 | 20 | T3.4, T3.5 | DS, AIC | TE
Test User Interface Design | T4.2 | 20 | T3.9 | FSD | TE
Remaining | 0
Project Management | 136
Research | 200
Development and Experimentation | 100
Testing and Evaluation | 40
9.375

## time estimations
TFG | 412.5 |  |  | 4 hours a day for 17 weeks working 7 days
WorkWeeks | 13 |  |  | 476
Hours per Week | 31.7308 |  |  | Risk Management
WorkDays | 7 |  |  | 26
Hours per Day | 4.533
GEP | 37.5
WorkWeeks | 4
Hours per Week | 9.375
WorkDays | 4
Hours per Day | 2.3438
| Project Objective (h) | Project Management Course (h) | Rounded Estimation (h) |  |  | Total (h) | Working Weeks | Hours per Week (h) | Working Days | Hours per Day (h)
Total Hours | 412.5 | 37.5 | 476 |  | Project Objective | 412.5 | 17 | 24.2647 | 7 | 3.4664
Working Weeks | 17 | 4 | 17 |  | Project Management Course | 37.5 | 4 | 9.375 | 7 | 1.3393
Hours per Week | 24.2647 | 9.375 | 28 |  | Rounded Estimation | 476 | 17 | 28 | 7 | 4
Working Days | 7 | 7 | 7
Hours per Day | 3.4664 | 1.3393 | 4

## Budget tables
hr_salary_plus_ss | Role | Annual Salary (€) | Annual Salary with Social Security (€) | Hourly Rate (€/h) |  | Avg. base salary
| Project Manager (PM) | 48452 | 65410.2 | 31.4472 |  | https://www.payscale.com/research/ES/Job=Project_Manager%2C_Information_Technology_(IT)/Salary
| Data Scientist (DS) | 35666 | 48149.1 | 23.1486 |  | https://www.payscale.com/research/ES/Job=Data_Scientist/Salary
| Full Stack Developer (FSD) | 22481 | 30349.35 | 14.591 |  | https://www.payscale.com/research/ES/Job=Web_Developer/Salary
| AI Consultant (AIC) | 53117 | 71707.95 | 34.475 |  | https://www.payscale.com/research/ES/Job=Senior_Data_Scientist/Salary
| weeks | 52
| hours per week | 40
| hours per year | 2080
human_cpa | Name | Task | Time (h) | PM (h) | DS (h) | FSD (h) | AIC (h) | Cost Per Task (€)
| Project Management | T1 | 136
| Tutor Meetings | T1.1 | 10 | 10 | 0 | 0 | 10 | 659.2219
| Contextualisation and Scope | T1.2 | 15 | 15 | 15 | 0 | 0 | 818.9373
| Project Planning | T1.3 | 12 | 12 | 0 | 0 | 0 | 377.3665
| Economic Management | T1.4 | 12 | 12 | 0 | 0 | 0 | 377.3665
| Sustainability Report | T1.5 | 12 | 12 | 0 | 0 | 0 | 377.3665
| Final Document Synthesis | T1.6 | 40 | 40 | 0 | 0 | 0 | 1257.8885
| Development Monitoring | T1.7 | 35 | 35 | 0 | 0 | 0 | 1100.6524
| Research | T2 | 200
| Study transformer Architecture | T2.1 | 60 | 0 | 60 | 0 | 0 | 1388.9163
| Familiarise with NLP techniques | T2.2 | 50 | 0 | 50 | 0 | 0 | 1157.4303
| Analyse Music Datasets | T2.3 | 50 | 0 | 50 | 0 | 0 | 1157.4303
| Explore Deep Learning Frameworks | T2.4 | 20 | 0 | 20 | 0 | 0 | 462.9721
| Investigate web development stacks | T2.5 | 20 | 0 | 0 | 20 | 0 | 291.8207
| Development and Experimentation | T3 | 100
| Create Development Environments | T3.1 | 5 | 0 | 5 | 0 | 0 | 115.743
| Exploratory Data Analysis (EDA) | T3.2 | 10 | 0 | 10 | 0 | 0 | 231.4861
| Build Experimentation Pipeline | T3.3 | 20 | 0 | 20 | 0 | 0 | 462.9721
| Train Model | T3.4 | 25 | 0 | 25 | 0 | 0 | 578.7151
| Fine-tune Model | T3.5 | 10 | 0 | 10 | 0 | 0 | 231.4861
| Design User Interface | T3.6 | 10 | 0 | 0 | 10 | 0 | 145.9103
| Implement User Interface | T3.7 | 10 | 0 | 0 | 10 | 0 | 145.9103
| Program API Server | T3.8 | 5 | 0 | 0 | 5 | 0 | 72.9552
| Deploy web application | T3.9 | 5 | 0 | 0 | 5 | 0 | 72.9552
| Testing and Evaluation | T4 | 40
| Evaluate Model | T4.1 | 20 | 0 | 20 | 0 | 20 | 1152.4716
| Test User Interface Design | T4.2 | 20 | 0 | 0 | 20 | 0 | 291.8207
|  |  | Hours per Role (h) | 136 | 285 | 70 | 30 | Total Cost (€)
|  |  | Cost per Role (€) | 4276.8208 | 6597.3526 | 1021.3724 | 1034.2493 | 12929.7951
general_costs
| Hardware | Initial Cost (€) | Life Expectancy (Years) | Yearly Usage (h) | Hours Used (h) | Amortisation (€)
| Laptop | 1200 | 5 | 2080 | 476 | 54.9231
[8 empty] | Initial Cost (€) | 1200
[8 empty] | Life Expectancy (Years) | 5
| Type | Cost (€) | [5 empty] | Yearly Usage (h) | 2080
| Hardware | [6 empty] | Hours Used (h) | 476
| Laptop amortization | 54.9231 | [5 empty] | Amortisation (€) | 54.9231
Space
| Electricity | 275
| Internet | 21.71
| Total GC | 351.6331
budget_contingency
|  | Estimated Cost (€) | Risk (%) | Cost (€)
| Project Deadline | 1100.6524 | 10 | 110.0652
| Inexperience in the Domain | 1388.9163 | 20 | 277.7833
| Poor Planning | 1100.6524 | 10 | 110.0652
| Computational Power | 578.7151 | 15 | 86.8073
|  |  | Total Cost | 584.721
Activity | Cost (€)
Total CG | 351.6331
Total CPA | 12929.7951
CPA Contingency | 1939.4693
Total Incidentals | 584.721
Total Budget | 15805.6184